# SwanCon 2007 Committee Meeting, 17th February 2006

Attendance: Michael, Tom, April, Tina, Erika, Paul

Apologies: Coman, Stephanie

### Agenda:

- Launch

  - Video

  - Progress Report

  - Tshirts

  - Chocolates

- Fundraising

- Guests

- Quiz Night

- Movie Screenings

###### Meeting opens 1905

### Launch:

Things that need to be finalised before our launch:

  - Video is going nicely – currently in editing phase. Dave Cake will be doing the sound. Hope to have it done before the con. Tom & Tina to do a quick job on the sound as a backup.

  - Progress Report

    - Convenor’s Report: Michael to write – will get people to approve

    - Events: Need to get a list together – movie screenings, quiz nights, games day.

    - Committee listing needs to be finalised

    - Prices – variation in prices needs to be approved by WASFF.

    - Bios – have bios from Russell, Damian and Matthew. Need to construct ones for Elizabeth and David from online info.

    - Competitions – need rules for Short Story and Fanvid competitions

  - Tshirts – need to have order enough for the launch. Decide on 30, plus committee shirts

  - Chocolates – Michael to order and bring to the con.

### Fundraising:

Chocolates and movie screenings will be primary form of fundraising. Michael will handle the chocolate orders, Thatcher will handle the screenings.

Chocolates will be sold at workplaces (GHD, DAA, Quokka, City of Swan libraries)

Entertainment Books – we should be pushing the $60 as they give us more profit.

What grants would we be able to apply for?

- ArtsWA? – may be a problem with 2005s acquittal

- Lotteries?

- Healthway? (Tai chi, DDR aerobics, martial arts etc)

### Guests:

We now have 2 International Guests of Honour – Elizabeth Moon and David Gerrold.

Both responded to our email very enthusiastically, and even don’t mind us only paying for their flights and not partners.

Keep in contact monthly for the next 6 months, then more frequently as required.

Make sure we ask them what they may be interested in talking about, wat they don’t want to talk about, allergies, requirements, etc.

### Quiz Night:

Quiz night – 23rd April, Hyde Park Hotel, 430pm onwards. Thatcher, Erika and Tommo will put together questions.

Paul to write a begging letter for distribution to shops.

### Movie Screenings:

Dave will organise with Jay times for screenings. First screening should be V for Vendetta. One screening a month is a good idea – more frequent will “burn” people out.

Next meeting 10th March, 2006.

###### Meeting Closed 2015