Meeting 170607
Present: Anna, Davina, Elaine, Peter, Jenny, Grant, Linda, Michael, 
Art.

Progress report:

Glenda – Will organise from her end airfares and we will reimburse.

Paul and Ken have been e-mailed this week, should expect to hear back 
from them next week otherwise will send another reminder.

Bank account – lunchtime Friday – 12.30 at Bankwest Tower

Hotel to be negotiated – Anna to send contract to Grant and Davina

Guests – only need to worry about airfares at this stage

Progress report to be done by end of week – Grant to do.

Advertise short film and short story comp – need to do as soon as 
possible. What's happened with advertising? Davina to follow up with 
Graham. Short stories comp to be advertised to schools still, Convert 
flier to poster to send out.

Quilts to still be done – Davina still organising.

Chocolates – Grant has two boxes to put into his workplace, Jenny can 
take a couple of boxes as well.

No point doing a progress report, until we know the hotel.

Healthways – to be asked for sponsorship?

Games Day (19th August) needs to be advertised – speak to Rob and 
Leece about getting involved – Jenny and Peter to work with Calum and 
contact Rob and Leece.

Linda to check venues in Town of Cambridge – Leederville. 1-5 Sunday 
the 19th. Will do drinks and food, Jen to get drinks and food. Will 
need a cash float on the day. Advertise as kid friendly so we can 
have kids there as well. Adults $5, Children $2

Quiz Day – Same venue as Games Day so that we can see if we can get a 
discount. 8 rounds of 10 questions. Two table sheets. 1 – 5 14th 
October. Tables of 8. Grant to confirm MC. Michael to collate 
questions. Everyone to send Michael 10 questions. Check venues for 
urns. 

Fantastic Planet to be approached to see if they want to offer us 
some prizes for the quiz night. Approach Empire, White Dwarf, Qulaity 
Comics. Ask Oxfam. Davina to ask places like the bowling alleys, 
record store etc for prizes. Contemplate doing platters for the 
tables if Jen can get donations from work. Do flier for both events 
at the same time. Entry fee to cover hall hire. Meet here (our place) 
7th October 3pm – 4pm to organise quiz prep and prizes etc.

Grant to organise major screenings for later on in the year.

Sponsors: BBC dragging their feet. Hatchett Lievore meeting next 
week. Orbit wanting to throw money at us. 

Send an e-mail to Tim. Can't make meetings, will really need people 
for week before and on registration desk. 

Next meeting 8th July 1pm – Grant's place.