Committee meeting: 15 July 2007

Opened: 6:25pm

Attendees: Elaine, Ju, PRK, Maia, Jess.

Apologies: Nil

Actions from last meeting: N/A

Correspondence:

- Letters sent to several hotels - Hyatt Regency, Novotel, All Seasons (Acacia), Mercure, Parmelia Hilton.

- Letters received from the Novotel and Hyatt.

- Email exchange with  Harper Collins regarding possible guests.

- We have spoken to and penciled in a national guest.

Guests:

- Pro/National guest tentatively confirmed. PRK to send official invitation to Pro & National Guest.

- Harper Collins have confirmed our desired guest is unavailable for 2009. Ongoing conversation regarding alternate guests is underway. PRK to continue discussions with HC re guests.

- IG 1 - pro comment, travels, "very cool", cyberpunk. PRK to contact IG1.

- IG 2 - feminist, elderly, brilliant on panels, involved in community. Hold for discussion pending outcome of inviting IG1.

- Lit Guest: Melbourne, possible funding from publisher. Elaine to sound out via email.

- Fan guest will be asked. Elaine to provide contact details to PRK, PRK to contact.

Budget:

- Need to start planning a budget. Elaine to contact Firebird for template.

- Grants for short story/art competitions? Short story competitions? Elaine to speak with contact re possible grants.

- No action on the bank account yet. Elaine and Ju have 100pt ID with Bank West. PRK to find out and action 100 point ID as required for account.

Hotel:

- Novatel: is big enough, and gave us prices. Very expensive, but possible to negotiate over packages. Ju to begin discussion based on package deal.

- Duxton is desirable, but previous attempts have been rebuffed. PRK to speak with Duxton function manager.

- Hyatt: not too good a layout. Also possible noise issues. Pricing rather expensive. Not action required unless everything else is unavailable.

- No information yet about All Seasons, Mercure and Hilton. Ju to follow up with All Seasons, Mercure and Hilton.

Other Business:

- Possible volunteer suggested. Not needed immediately, but definitely useful later on. PRK to speak with possible volunteer to determine time frames / activities.

Action list:

PRK

- PRK to send official invitations to Professional and National guest.

- PRK to continue discussions with HC re additional guests.

- PRK to contact IG1 and invite.

- PRK to contact Fan Guest after details provided by Elaine.

- PRK to arrange 100pt ID with Bank West and follow up Bank Account information with WASFF.

- PRK to speak with Duxton function manager.

- PRK to speak with possible volunteer to determine time frames / activities.

Elaine:

- Elaine to sound Lit Guest via email re attendance & publisher funding.

- Elaine to provide Fan Guest contact details to PRK.

- Elaine to contact Firebird for Budget Template.

- Elaine to speak with contact re possible grants for story competitions / art show.

Ju:

- Ju to begin discussions with the Novotel based on a package deal.

- Ju to follow up with All Seasons, Mercure and Hilton.

Closed: 7:40pm.

Next meeting: To be scheduled when more information arrives.