Minutes

27 January 2008

Meeting opened: 2:13pm

Attendees: PRK, Ju Whitehead, Jess Bridges, Maia Bobrowicz, Elaine Kemp, Stephanie Bateman-Graham, Christopher Phillips, Kathryn Linge.

Apologies:  Nil

Future absences: Jess will be in New Zealand between 18 Feb – 3 March.

Confirming minutes of last meeting: Maia, Jess seconded.

Introductions for new members

Actions from last meeting:

Guests/Coordinators:

- PRK was formally inviting the Fan Guests; (who have both accepted).

- PRK was following up on the Lit Guest’s funding situation with the publisher; (email has been sent) and talking to Voyager (exploring possible guest) and Hachette Livra publishers (not yet).

- Elaine was sounding out possible academic coordinator. (Has been sourced)

Budget:

- Elaine has paperwork about bank account and the cheque book.

- Elaine was setting up budget organisation and float for last day Swancon 2008 (not until closer to 2008 con. Cash book is in the works).

Hotel:

- Ju: update on plan A – Seasons of Perth, and Miss Maud, with possible back up with Yirri Yarkin Threatre.  (Are now 2nd or 3rd preferences.)

Artwork and Website:

- Ju was sounding people out to do website and logo etc. work. Needs to find Marketing, sponsorship and a ‘volunteer to wrangle to volunteers’ people.

Welcome Stephanie, Kathryn and Christopher!

Correspondence:

- Email within list

- Have received hotel packages.

Venue:

- First preferred option: Ambassador hotel (primary), Good Earth hotel (secondary). Food should be covered well. We’ll take it if it’s anywhere close to $20,000, and it’s a strong possibility. Ju will follow this up

- All Seasons and Seasons of Perth are tying for second place.

Budget:

- Draft budget total is $52,000. We’re awaiting a venue, and then we can start doing things in earnest.

Membership:

- Hotel prices go up means membership goes up.

- Launch $130 standard, $120 concession. Could raise by $10 for the launch.

- $150 for year, $135 concession... (Cheaper than the eastern states)

- Or we shorten the Con, which is an option. Dropping Thursday would take a fifth of our budget, for example.

Guests:

- PRK to get bios from people.

- If we want another international guest to pull in more membership, can it work in the budget? If we can bring down the hotel, or find the money somewhere else. Possible tie-in with eastern states cons to reduce travel costs.

Launch:

- PRT (progress report 0) to be handed out at the launch.

- Session with slide presentation, explain our theme, having video of our guests in our presentation. Official things will take half an hour-ish. PRK will MC.

- T-shirts, for which we need artwork.

- We will need lollies for the launch, raffle tickets.

Logo:

- Text will read “Swancon 2009” rather than 34, and include Perth, Australia.

- Kathryn will continue with the logo, making the hand more robotic/alien – a three fingered Terminator-style hand.

Website:

- Will include:

  - membership and dates of price rises,

  - committee contact details,

  - links to downloadable documents.

  - 2008 wrap-up, and 2009 going live immediately after.

  - Suggestion page for panels

  - link to WASFF.

Fundraising:

- T-shirts at the launch, and during the Con.

- No other actual merchandise.

- Raffle for a membership.

Last day of Swancon 2008 roster:

- 9-11am: Maia and Elaine,

- 11-1pm: Ju and Steph and Jess.

- 1-3pm: PRK (and Mel?)

- 3-5pm: Maia and Elaine

Other business:

- Programme will be spelled ‘program’.

Action list:

PRK

- Will ask for membership booklets at WASFF meeting

- Ask guests what their T-shirt sizes are and get their bios.

Elaine

- To investigate T-shirt prices

- Pursue working spreadsheets

Ju

- Venue follow-up.

- Sourcing people for marketing, volunteer wrangler and sponsorship volunteers.

Kathryn

- Continuing work on the logo – making the hand more robotic.

- Starting progress report 0 – See Ju for information

Christopher

- Will draft a site on his own server.

- Will check with current web hoster to see if they meet our needs

Meeting closed: 4:51pm

Next meeting: Sunday 10th Feb 2008 2pm @ Elaine’s. (363 Lord Street, Beechboro)